## Slide 1: STEM for inclusive schools School Education ERASMUS+ KA220-NW-23-30-151162 Cooperation partnerships in school education
Reference Number: 2023-1-DE03-KA220-SCH-000151162
Duration: 03.09.2023 to 02.03.2026 (30 months)
Chair of Business and Human Resource Education II Prof. Dr. Marc Beutner
STEM for inclusive schools
Transnational Partner Meeting - TPM 2 Pedagogical Conference – Poland - Radom 3rd to the 5th of September 2024
Current Status 4th of September 2024
Presentation of the leading partner: University of Paderborn

## Slide 2: Workpackages of STEM for inclusive schools
WP 1 – PROJECT MANAGEMENT
WP 2 – STEM ACTIVITIES DESIGN AND OER
WP 3 – TOOLKIT AND DIGITAL TOOL FOR MEASUREMENT AND EVALUATION
WP 4 – GUIDEBOOK FOCUSED ON INCREASING STEM PARTICIPATION
Ongoing
Ongoing
Starts in October 24
Universitatea Dunarea de Jos din Galati, Sucessos, SIEC and all partners
UPB and all partners
SIEC, UPB and all partners
Starts in May 25
SIEC and all partners

## Slide 3
The WPs of STEM for inclusive schools
WP2: STEM ACTIVITIES DESIGN AND OER
WP1: Project Management - ongoing task
WP3: TOOLKIT AND DIGITAL TOOL FOR MEASUREMENT AND EVALUATION
WP4: OK FOCUSED ON INCREASING STEM PARTICIPATION
WP3a: Toolkit Development
WP3b: Digital Tool Construction
WP2a: Questionnaire and focus group interview questions
WP2b: Course Activity Designs According to Learning Models
WP2c: OER design

## Slide 4: 4 Transnational Partner Meetings - TPMs
TPM 1 – Kick-off - Romania
TPM 2 – Progress I - Poland
TPM 3 – Progress II - Portugal
TPM 4 – Final - Germany
11th, 12th and 13th of March 2024
03rd, 04th and 5th of September 2024
6th, 7th and 8th of May 2025
16th, 17th and 18th of December 2025
Fixed dates agreed at the LTTA in Paderborn, Germany – see minutes which Fatima provided
Done
Ongoing

## Slide 5: 3 Learning Teaching Training Activities - LTTAs
LTTA 1 – Inclusive Learning Models and Use of Digital Technologies in STEM – Germany
LTTA 2 – Methods and Techniques for
Measuring and Evaluating Transversal Skills and Learning Outcomes – Romania Uni
03rd to the 07th of June 2024
25th to 29th of November 2024
LTTA 3 – LTTA - Strategies and approaches to increase participation in STEM – Romania Scoala Gimn nr 7
22nd to 26th of September 2025
Done
Coming soon

## Slide 6: Regular short online meetings every 4 weeks
1. Online Meeting
12th of July 2024
Done
2. Online Meeting October 2024
01st of October 2024
Suggestion: every first Tuesday each month at 09.30 CET
3. Online Meeting November 2024
05th of November 2024
4. Online Meeting December 2024
03rd of December 2024
5. Online Meeting January 2025
07th of January 2025 …

## Slide 7: Report from Remi concerning WP2
https://drive.google.com/drive/folders/1M3MCjbSkOAqxfV5KUjs4LnNIQGoL-BxX?usp=drive_link

## Slide 8
Prof. Dr. Marc Beutner
Tel: +49 (0) 52 51 / 60 - 23 67
Fax: +49 (0) 52 51 / 60 - 35 63
E-Mail: marc.beutner@uni-paderborn.de
Universität Paderborn
Department Wirtschaftspädagogik Lehrstuhl Wirtschaftspädagogik II Warburger Str. 100
33098 Paderborn
http://www.upb.de/wipaed
Contact