## Slide 1: STEM for inclusive schools School Education ERASMUS+ KA220-NW-23-30-151162 Cooperation partnerships in school education
Reference Number: 2023-1-DE03-KA220-SCH-000151162
Duration: 03.09.2023 to 02.03.2026 (30 months)
Chair of Business and Human Resource Education II Prof. Dr. Marc Beutner
STEM for inclusive schools
Transnational Partner Meeting - TPM 2 Pedagogical Conference – Poland - Radom 3rd to the 5th of September 2024
What´s laying ahead of us?
Presentation of the leading partner: University of Paderborn

## Slide 2: LTTA Romania - University
LTTA 2 – Methods and Techniques for
Measuring and Evaluating Transversal Skills and Learning Outcomes – Romania Uni
25th to 29th of November 2024

## Slide 3: TPM 3 Portugal
TPM 3 – Progress II - Portugal
6th, 7th and 8th of May 2025

## Slide 4: Work on the Activities of WP and basis for WP3
Finish the materials for your five activites and upload in GoogleDrive
until the 15th of October 2024
Translation of all activities from Englisch to your local language
until the 15th of November 2024
Integration of all materials into the website / learning platform
until the 15th of January 2025

## Slide 5: WP3 TOOLKIT AND DIGITAL TOOL FOR MEASUREMENT AND EVALUATION
Information about Toolkit-Development Information by Universitatea
Dunarea de Jos din Galati
until the 15th of November 2024
Work on the Toolkit-Development and Construction by Universitatea Dunarea de Jos din Galati, Innovatif, UPB, Scoala Gimnaziala Nr. 7 Galati, SIEC
Finished until the 31st of March 2025
Piloting and Reporting by Universitatea Dunarea de Jos din Galati, Innovatif, UPB, Scoala Gimnaziala Nr. 7 Galati, Successos
Finished until the 30th of April 2025

## Slide 6: Dissemination
Ongoing Dissemination tasks (poster, leaflets, newspaper articles, direct presentation, events, days of open door etc.) in each country
+
National dissemination activities, events
programs, signature chart, distributed
certificates, visual-auditory materials; activity,
expenditure and dissemination reports, at
least 15 people participating in the activity.
a) until the 30th of September 2024 (WP 2)
b) until the 30th of April 2025 (WP 3)
Ongoing

## Slide 7
Prof. Dr. Marc Beutner
Tel: +49 (0) 52 51 / 60 - 23 67
Fax: +49 (0) 52 51 / 60 - 35 63
E-Mail: marc.beutner@uni-paderborn.de
Universität Paderborn
Department Wirtschaftspädagogik Lehrstuhl Wirtschaftspädagogik II Warburger Str. 100
33098 Paderborn
http://www.upb.de/wipaed
Contact