## Slide 1: STEM for inclusive schools School Education ERASMUS+ KA220-NW-23-30-151162 Cooperation partnerships in school education
Reference Number: 2023-1-DE03-KA220-SCH-000151162
Duration: 03.09.2023 to 02.03.2026 (30 months)
Chair of Business and Human Resource Education II Prof. Dr. Marc Beutner
STEM for inclusive schools
Transnational Partner Meeting - TPM 1 The Kick-off-Meeting 11th to the 13th of March 2024
Insight into WP 2 – STEM ACTIVITIES DESIGN AND OER 12th of March 2024
Presentation of the leading partner: University of Paderborn

## Slide 2: Insight into WP 2 – STEM ACTIVITIES DESIGN AND OER Activities under WP2
2.1: Transnational Project Meeting: Opening Meeting – TPM1 Galati Romania – 11 - 13-03-2024 Universitatea Dunarea De Jos Din Galati, RO
2.2: Collecting Data & Field Research SIEC Badawcza Lukasiewicz – Instytut Technologii Eksploatacji, PL
2.3: LTTA Inclusive Learning Models and Use of Digital Technologies in STEM UPB – Universität Paderborn, DE
2.4: Identifying Lesson Activity Designs According to Learning Models UPB – Universität Paderborn, DE
2.5: Preparation of STEM Lesson Activities According to Learning Models UPB – Universität Paderborn, DE
2.6: OER design and construction Sucessos Criativos, Lda, PT
2.7: Transnational Project Meeting-2: Progress Meeting – „The STEM conference for School education“ Poland SIEC Badawcza Lukasiewicz – Instytut Technologii Eksploatacji, PL
2.8: Piloting and Reporting SIEC Badawcza Lukasiewicz – Instytut Technologii Eksploatacji, PL
Notes: More restrictive

## Slide 3: Insight into WP 2 – STEM ACTIVITIES DESIGN AND OER Dissemination Activities under WP2
2.9.1: Dissemination Activities – Germany UPB – Universität Paderborn, DE
2.9.2: Dissemination Activities - Romania I Universitatea Dunarea De Jos Din Galati, RO
2.9.3: Dissemination Activities - Romania II Scoala Gimnaziala Nr. 7 Galati, RO
2.9.4: Dissemination Activities – Poland SIEC Badawcza Lukasiewicz – Instytut Technologii Eksploatacji, PL
2.9.5: Dissemination Activities – Türkiye Inovatif ve Girisimci Toplum Dernegi, TR
2.9.6: Dissemination Activities – Portugal Sucessos Criativos, Lda, PT
Notes: More restrictive

## Slide 4: Insight into WP 2 – STEM ACTIVITIES DESIGN AND OER 2.3: LTTA Inclusive Learning Models and Use of Digital Technologies in STEM UPB – Universität Paderborn, DE
Complex
Process oriented
Social
Practical
Holistic
STEM
Engage
Explore
Explain
Elaborate
Evaluate
Concrete
Experience
(CE)
Reflective
Observation
(RO)
Abstract
Conceptualisation
(AC)
Active
Experimentation
(AC)
5E-STEM after Vu Thi Ha / Le Hong Chung / Nguyen Van Hanh / Bui Minh Hai (2023)
The experiential Learning Cycle after Kolb, D. A. 1984
The pedagogic principles according to Stracke, et.al. 2019
+
+
Notes: More restrictive

## Slide 5: Insight into WP 2 – STEM ACTIVITIES DESIGN AND OER 2.4: Identifying Lesson Activity Designs According to Learning Models UPB – Universität Paderborn, DE
Various student activities contribute to the learning process. These activities encompass reading journal articles, textbook chapters, and lecture materials, as well as writing papers and essays. Additionally, participating in discussions, taking tests, giving presentations, conducting surveys, making observations, and running experiments all play a role in enhancing knowledge and understanding.
Elements of the lesson activity:
Presentation (20 pages)
At least 3 integrated classroom tasks (on group task, one partner task and one work alone task)
2 infographics and 1 video
5 H5P online learning tasks (Free version: https://h5p.org; chargeable version: https://h5p.com/
Take all three models into account!
Notes: More restrictive

## Slide 6: Insight into WP 2 – STEM ACTIVITIES DESIGN AND OER 2.5: Preparation of STEM Lesson Activities According to Learning Models UPB – Universität Paderborn, DE
Act 2.5: According to the activity templates, partners (exc. P6) will design at least 5 STEM activities with digital content and sustainability
Template will be provided in March 2024 after the agreement on the activities at this meeting (TPM1)
Notes: More restrictive

## Slide 7
Prof. Dr. Marc Beutner
Tel: +49 (0) 52 51 / 60 - 23 67
Fax: +49 (0) 52 51 / 60 - 35 63
E-Mail: marc.beutner@uni-paderborn.de
Universität Paderborn
Department Wirtschaftspädagogik Lehrstuhl Wirtschaftspädagogik II Warburger Str. 100
33098 Paderborn
http://www.upb.de/wipaed
Contact