## Slide 1: STEM for inclusive schools School Education ERASMUS+ KA220-NW-23-30-151162 Cooperation partnerships in school education
Reference Number: 2023-1-DE03-KA220-SCH-000151162
Duration: 03.09.2023 to 02.03.2026 (30 months)
Chair of Business and Human Resource Education II Prof. Dr. Marc Beutner
STEM for inclusive schools
Transnational Partner Meeting - TPM 1 The Kick-off-Meeting 11th to the 13th of March 2024
What´s laying ahead of us? 12th of March 2024
Presentation of the leading partner: University of Paderborn

## Slide 2: Next steps until the next meeting
LTTA 1 – Inclusive Learning Models and Use of Digital Technologies in STEM – Germany
Suggested date:
8th to 12th of April 2024
To Do | Date
WP2– Questionnaire and Interviews A2.2 Collection of data and field research | 31.03.2024
WP2 – Activities A2.5 Preparation of STEM Lesson Activities according to Learning Models | 30.09.2024
WP2 – OER A2.6 OER design and construction | 30.09.2024
Dissemination – 1 Poster, 1-2 Press releases, Direct contacts | 31.07.2024
TPM 2 – Progress I - Poland
Suggested date:
13th to 15th of Aug 2024
Notes: More restrictive

## Slide 3
Prof. Dr. Marc Beutner
Tel: +49 (0) 52 51 / 60 - 23 67
Fax: +49 (0) 52 51 / 60 - 35 63
E-Mail: marc.beutner@uni-paderborn.de
Universität Paderborn
Department Wirtschaftspädagogik Lehrstuhl Wirtschaftspädagogik II Warburger Str. 100
33098 Paderborn
http://www.upb.de/wipaed
Contact